## Sheet1
Legend:
| Project Start Date: |  | 2022-10-17 |  |  |  |  | On Track |  |  |  | Low Risk |  |  |  | Med Risk |  |  |  | High Risk
Gantt Chart
[6 empty] | October | [15 empty] | November | [29 empty] | December
[6 empty] | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
Milestone Description | Category | Assigned To | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Set up NextJS project and create Tailwind template | On Track | Andrew | 100% | 2022-10-17 | 6 | bar: Week 1 M to Week 1 S
Set up MongoDB and create fields for user info | Postponed | Ian | 100% | 2022-10-17 | 10 | bar: Week 1 M to Week 4 S
Add Login/Logout UI | On Track | Andrew | 100% | 2022-10-17 | 6 | bar: Week 1 M to Week 1 S
Add Login/Logout functionality in the backend | Low Risk | Ian | 100% | 2022-10-17 | 12 | bar: Week 1 M to Week 2 F
Create Landing Page UI | On Track | Andrew | 100% | 2022-10-17 | 8 | bar: Week 1 M to Week 2 M
Create Schedule Appointments View & connect user appointments to DB | Low Risk | Ian | 0% | 2022-10-31 | 14 | bar: Week 3 M to Week 4 S
Add notification system based on user appointments | On Track | Andrew | 0% | 2022-10-31 | 14 | bar: Week 3 M to Week 4 S
Add Track Exercise View & connect user exercises to DB | Medium Risk | Ian | 0% | 2022-11-14 | 14 | bar: Week 5 M to Week 6 S
Add Track Diet View & connect user diet to DB | Medium Risk | Ian | 0% | 2022-11-14 | 14 | bar: Week 5 M to Week 6 S
Incorporate appointments, exercise, and diet info into landing page | On Track | Andrew | 0% | 2022-11-28 | 14 | bar: Week 7 M to Week 8 F
Deploy to Gitlab Pages | On Track | Ian | 0% | 2022-11-28 | 14 | bar: Week 7 M to Week 8 F